## RTM
RTM Report
|  |  |  | Project Name | Tutorials Ninja
|  |  |  | Client | Tutorials Ninja
|  |  |  | Created by | Vinita & Alok
|  |  |  | Creation date | 2025-01-17
|  |  |  | Approved Date | 2025-01-19
Requirement_ID | Requirement Description | Priority | Test Case ID | Test Case Description | Status | Remarks
Req_001 | User should be able to register successfully. | High | TC_001 | Verify registration with valid details. | Passed | Tested on Jan 18, 2025.
Req_002 | User should be able to log in with valid credentials. | High | TC_002 | Verify login with valid username and password. | Passed | Login successful with valid inputs.
Req_003 | Search functionality should work correctly. | Medium | TC_003 | Verify searching products by name or keyword. | Fail | Search not returned correct results.
Req_004 | User should be able to add items to the cart. | High | TC_004 | Verify adding a single product to the shopping cart. | Passed | Added item displayed in the cart.
Req_005 | User should be able to checkout successfully. | High | TC_005 | Verify successful checkout after adding items to cart. | In Progress | Payment gateway issue encountered.
Req_006 | User should be able to create a wishlist. | Medium | TC_006 | Verify adding products to the wishlist. | Passed | Wishlist saved products successfully.
Req_007 | Contact Us form should send user inquiries. | Low | TC_007 | Verify sending a query through the Contact Us form. | Passed | Confirmation email received.
Req_008 | Order History should display past orders. | High | TC_008 | Verify order history displays previous orders. | Fail | Past orders loaded unsuccessfully.